## Sheet1
Date | Event/Area | Actions | Person | Budget | Comments
2019-08-01 | MAW (Make-a-Wish) | Contact Helene Peterson to get our MAW kid | Mrs. Fenwick |  | Need to get on this early since our assembly is the first of October
2019-08-10 | Fundraising | Order Suckers | Mrs. Fenwick |  | Start fundraiser the second week of school for students who are ready to start selling
2019-08-19 | MAW (Make-a-Wish) | Pick MAW Theme, work with student council and video broadcasting | Students/Mrs. Fenwick |  | 3rd year students, second week of school
2019-08-19 | MAW (Make-a-Wish) | Get Blas on board to announce assembly | Mrs. Fenwick
2019-08-26 | Committee Assignments | 3rd year students will decide on and for teams for DECA campaigns | Students |  | Done in class - may take multiple days
2019-09-01 | Officer Meeting | Define duties, decide on BASIC training, what kind of leaders to they want to be? | Officers/Mrs. Fenwick |  | **Do off campus - fun activity/bonding/brain storming
2019-09-01 | Wahooz Membership Day | Set date and organize busses | Mrs. Fenwick |  | Should be after MAW
First week of Semptember | DECA Member meeting | Purpose: talk dues, Wahooz, and business sponsors, MAW Goals, MAW shirt design (srs) | Mrs. Fenwick/DECA members |  | lunch meeting/create a hand out for those who can't make it
2019-09-15 | Social Media Update | Purpose is to celebrate and update the community on what our chapter is up to. Highlight members who have gone above and beyond. | Hava and Charley |  | This will be a regular montly post in addition to other posts
2019-09-15 | Buisness sponsor ship letters | Ensure all students have access to this information and know how to obtain a business sponsor | Mrs. Fenwick |  | Part of daily agenda in class
2019-10-01 | DECA Dues | Due today! $18 to be a National DECA member |  |  | This will have been discussed at the first meeting. Deal for those who want a DECA shirt and a MAW shirt. $35 for all three
2019-10-03 | MAW assembly | Assembly, miracle minute, stars, etc. EVERYTHING! | DECA, Marketing Students, Student Council |  | This will be a huge push all through September, utilizing both class time for all students and my third year students who plan everything
Second week of October | DECA member meeting | Purpose: Business sponsers due, celebrate MAW |  |  | Could make this meeting happen at the Wahooz day??
Mid October | Buisness Sponsors | They are due! | DECA students |  | **Make sure to have shirts made prior to Wahooz
2019-10-15 | Social Media Update | Purpose is to celebrate and update the community on what our chapter is up to. Highlight members who have gone above and beyond. | Hava and Charley |  | This will be a regular montly post in addition to other posts
Late October | Wahooz Membership Day |  | All DECA members
2019-11-01 | Toy Drive | Contact Elementary schools | Mrs. Fenwick |  | Valley View or Mountain View (Abraham)
2019-11-01 | Scentsy Fundraiser |  | Mrs. Fenwick/DECA members |  | Makes great x-mas presents and DECA gets 30% of sales
First week of Novemeber | Deca Member Meeting | Purpose: Upcoming fundraisers include toy drive and scentsy
2019-11-15 | Food Drive | Assist Student Council | DECA members
2019-11-15 | Social Media Update | Purpose is to celebrate and update the community on what our chapter is up to. Highlight members who have gone above and beyond. | Hava and Charley |  | This will be a regular montly post in addition to other posts
First week of December | DECA Member Meeting | Purpose: Touch base on fundraisers, toy drive, start thinking about DDD, progress of State compeitiors, start talking ICDC |  |  | Lunch Meeting
2019-12-03 | DECA Campaigns | Are due! | 3rd year DECA members
2019-12-15 | Social Media Update | Purpose is to celebrate and update the community on what our chapter is up to. Highlight members who have gone above and beyond. | Hava and Charley |  | This will be a regular montly post in addition to other posts
2019-12-10 | Daddy Daughter Dance (DDD) | Advertise: Save the date flier to elementary schools, social media | Social media director & public relations director (Charley and Hava)
2019-12-01 | DECA State Sign up | Start getting registered | Sudents interested in Comp. at State |  | Hopefully students already have an idea of what they plan to compete in
2019-01-10 | SBE | SBE recertification is due | Emma M. (VP SBE) |  | 3rd year - will submit online
Beg of January | DECA Member Meeting | Purpose: State and DDD | Mrs. F and Members |  | Lunch meeting
January | DECA state comp | Students will be working on their reports | Competiting Students, Mrs. Fenwick, Mrs. Murin (coming back to help)
2020-01-15 | Social Media Update | Purpose is to celebrate and update the community on what our chapter is up to. Highlight members who have gone above and beyond. | Hava and Charley |  | This will be a regular montly post in addition to other posts
January | Community Service Event | TBD - Start Planning | Members
2020-02-01 | DECA Member Meeting | Purpose: State registration due, go over schedule at state, financial update, plan community service event |  |  | Lunch Meeting
2020-02-02 | SCDC | Registration Due | Members
2020-02-15 | Social Media Update | Purpose is to celebrate and update the community on what our chapter is up to. Highlight members who have gone above and beyond. | Hava and Charley |  | This will be a regular montly post in addition to other posts
2/24/20-2/26 | Idaho State Career Development Conference | Compeition! | Competiting DECA students
March | Community Service Event | Actual Event
2019-03-05 | DECA Member Meeting | Purpose: Rummage Sale, Results from State, ICDC, finalize volunteers for DDD | Members |  | The majority of this meeting will be dedicated to those traveling to ICDC. Ideally parents will attend. We will talk expenses, schedule, rules etc.
2020-03-12 | ICDC | Idaho - final payment is due
2020-03-14 | DDD | Date of | Members/Mrs. Fenwick
2020-02-15 | Social Media Update | Purpose is to celebrate and update the community on what our chapter is up to. Highlight members who have gone above and beyond. | Hava and Charley |  | This will be a regular montly post in addition to other posts
April | Fundraising | Rummage Sale this month!
Early April | DECA Member Meeting | Purpose: Details for ICDC | Members |  | This meeting will be for those traveling to ICDC. All last minute updates and details.
2020-04-15 | Social Media Update | Purpose is to celebrate and update the community on what our chapter is up to. Highlight members who have gone above and beyond. | Hava and Charley |  | This will be a regular montly post in addition to other posts
4/29-5/2 | ICDC - Nashville | Competing students travel to Nashville for comp
May | Officers | Applications for following year | Interested students
May | ICDC Video | Seniors make a video of ICDC as a present to the DECA member who went |  |  | This can also be a great promotional tool
May | Celebration | End of year DECA celebration | Members |  | Not sure what this will look like yet, I don't believe they have done one in the past??